## Schedule
General Proposal Timeline & Milestones
SCSU Proposal #: | [6 empty] | Date SPAR notified of intent to submit: |  |  |  | 2019-01-01
Name of PI/PD | [6 empty] | Number of days to Submission: |  |  |  | 180
[7 empty] | days between internal milestones |  |  |  | 12.1429
| Dates for internal milestones | [7 empty] | 10 days to deadline | 5 days to deadline | Proposal Submission date:
Milestone | 2019-03-10 20:34 | 2019-03-23 | 2019-04-04 03:26 | 2019-04-16 06:51 | 2019-04-28 10:17 | 2019-05-10 13:43 | 2019-05-22 17:09 | 2019-06-03 20:34 | 2019-06-16 | 2019-06-23 | 2019-06-30
PI/PD notifys SPAR of intent to submit
SPAR assigns Proposal #, reviews RFP
Study Guidelines
SPAR & PI/PD confirm submission plan
PI/PD drafts budget
PI/PD drafts proposal
Begin completion of forms
Gather Support Materials
Budget reviewed & finalized | bar: 2019-05-22 17:09 to 2019-06-03 20:34
Review Support Materials Checklist
Final proposal draft complete | bar: 2019-06-23
Begin Approval Routing
Submit Proposal Package to sponsor